## Product Backlog
User Story Number | User Story | Acceptance Criteria | Priority (Sprint Backlog) | Requirements Reference | Revised Priority | Status
HI-001 | Should be verified by a Physician. | Conversation Content: 0.1 Chatbot Features | Sprint 6 | General Adaptation Syndrome (GAS) Mind Charity Foundation: Information & Support - "Helping someone else" | Sprint 7 | Cancelled
HI-002 | Should be anthropomorphic whilst not utilizing Machine Learning/Advanced Artificial Intellligence. | Typing Emulation: The Following are characteristics that Emulate Human Chatting Behaviors: 1.1 Words per Minute [300] 1.2 Chat Response Delay [2.5 sec Max] 1.3 Chat Bubble | Sprint 1 | Natural Conversation Flow |  | Completed
HI-003 | Should be user-friendly/easy to use. | Input Fields: The Following should be Available but not limited to: 2.1 Textbox - For instances requiring text based input. 2.2 Button - Submit Button to confirm user input. 2.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 2.4 Date - For input that requires Custom Date. | Sprint 1 | Chatbot Feature Structure: Homework Help Motivational Advice Event Reminder Seek Professional Help Venting Mode Technology Acceptance Model |  | Completed
HI-004 | Should be connected to Google Sheets and collect data via conversation. | Input Fields: The Following should be Available but not limited to: 3.1 Textbox - For instances requiring text based input. 3.2 Button - Submit Button to confirm user input. 3.3 Email - For input that requires user Email. | Sprint 2 | Event Reminder |  | Cancelled
HI-005 | Should redirect User to a Physician/Emergency Hotline. | Input Fields: The Following should be Available but not limited to: 4.1 Button - Submit Button to confirm user input. | Sprint 3 | Chatbot Feature: Seek Professional Help |  | Completed
HI-006 | Should not collect any kind of Sensitive/Personal Data. | Data Handling: 5.1 Cached Data - All sensitive user input are Cached Data | Sprint 2 | Chatbot Feature: Venting Mode Republic Act No. 10173 "Data Privacy Act of 2012" |  | Completed
HI-007 | Should be located on top of the Screen. | Input Fields: The Following should be Available but not limited to: 6.1 Button - Submit Button to confirm user input. | Sprint 2 | Navigation Bar |  | Completed
HI-008 | Should utilize Dialogue Management System/Pre-defined Conversation. | Interface: 7.1 Chat Simulation UI | Sprint 1 | Chatbot System |  | Completed
HI-009 | Should utilize Typebot's Built-in System. | Data Handling: 8.1 Data Table - All Data stored in Tabular form. | Sprint 5 | Undefined |  | Completed
HI-010 | Should utilize Google Sheets | Data Handling: 9.1 Data Table - All Data stored in Tabular form. 9.2 Column - Follow Naming Standards | Sprint 2 | Data Management |  | Completed
HI-011 | Should utilize Google Sheets for user data and send Email Reminder on designated Date. | Automation: 10.1 Script - Contains the Python Program for Email Automation. | Sprint 5 | Event Reminder Automation |  | Cancelled
HI-012 | Should contain Fill-up Form and be able to send Email to Business Email. | Input Fields: The Following should be Available but not limited to: 11.1 Textbox - For instances requiring text based input. 11.2 Button - Submit Button to confirm user input. 11.3 Email - For input that requires user Email. | Sprint 3 | Contact Us | Spint 4 | Completed
HI-013 | Should contain a Survey regarding the Chatbot via Google Forms. | Input Fields: The Following should be Available but not limited to: 12.1 Textbox - For instances requiring text based input. 12.2 Button - Submit Button to confirm user input. 12.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 12.4 Date - For input that requires Custom Date. | Sprint 6 | Feedback | Sprint 7 | Cancelled
HI-014 | Should have a welcome splash screen. | Animation: 13.1 Logo - Contains the Chatbot Logo. 13.2 Button - Submit Button to confirm user input. | Sprint 3 | Splash Screen | Sprint 5 | Completed
HI-015 | Should record the number of times user clicks on a certain feature and reflect on the Database. | Data Handing: 14.1 Data Table - All Data stored in Tabular form. 14.2 Column - Follow Naming Standards. | Sprint 5 | Analytics | Sprint 7 | Completed
HI-016 | Should have a log-in system for Admins to view Analytics. Users will remain anonynmous, not requiring log-in. | Input Fields: The Following should be Available but not limited to: 15.1 Textbox - For instances requiring text based input. 15.2 Button - Submit Button to confirm user input. 15.3 Email - For input that requires user Email. | Sprint 6 | Log-in System |  | Completed
HI-017 | Should have a Dashboard UI for Admins that shows a summary of the Analytics. | Visualization: 16.1 Graphics - For instances requiring visualization of data. 16.2 Summary - For quick rundown view of analytics. | Sprint 6 | Dashboard | Sprint 7 | Completed
HI-018 | Should utilize NLP/OpenAI Integration to avoid monotonous conversations. | Chatbot Response: 17.1 Varied Responses - The responses of the Chatbot should not be scripted. | Sprint 6 | Chatbot Algorithm |  | Completed

## Sprint Backlog
Sprint 1 Timeline: April 10 - 21
Sprint Goal: Build the Basic Structure of the Chatbot | User Story Number | User Story | Tasks | Acceptance Criteria/Tasks | Assignee/s | Remarks (User Story Point)
| HI-002 | Should be anthropomorphic whilst not utilizing Machine Learning/Advanced Artificial Intellligence. | 1. Set-up Chatbot Typing Emulation 2. Conduct Test Run | Typing Emulation: The Following are characteristics that Emulate Human Chatting Behaviors: 1.1 Words per Minute [300] 1.2 Chat Response Delay [2.5 sec Max] 1.3 Chat Bubble | Front-end/Back-end Developers | 12 hrs
| HI-003 | Should be user-friendly/easy to use. | 1. Study "Mind Charity Foundation: Information & Support Guides" 2. Implement Realistic Conversation Flow for each Listed Features 3. Conduct Test Run | Input Fields: The Following should be Available but not limited to: 2.1 Textbox - For instances requiring text based input. 2.2 Button - Submit Button to confirm user input. 2.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 2.4 Date - For input that requires Custom Date. | Front-end/Back-end Developers | 72 hrs
| HI-008 | Should utilize Dialogue Management System/Pre-defined Conversation. | 1. Use Dialogue Management System in designing the Chatbot Flow | Interface: 7.1 Chat Simulation UI | Front-end/Back-end Developers | 72 hrs
Sprint 2 Timeline: April 24 - May 5
Sprint Goal: Basic Webpage Development & Implementation of other Chatbot Features | User Story Number | User Story | Tasks | Acceptance Criteria/Tasks | Assignee/s | Remarks (User Story Point)
| HI-006 | Should not collect any kind of Sensitive/Personal Data. | 1. Loop Conversation Flow until User wishes to continue 2. Ensure no Personal Data is collected. 3. Conduct Test Run | Data Handling: 5.1 Cached Data - All sensitive user input are Cached Data | Back-end Developers | 48 hrs
| HI-010 | Should utilize Google Sheets | 1. Create a "Company Email" 2. Create Data Table following Standards using Google Sheets using Company Email | Data Handling: 9.1 Data Table - All Data stored in Tabular form. 9.2 Column - Follow Naming Standards | Back-end Developers | 3 hrs
| HI-004 | Should be connected to Google Sheets and collect data via conversation. | 1. Connect Chatbot to Google Sheets 2. Give edit access to Google Sheets 3. Create Conversation for collecting User Input Data 4. Conduct Test Run | Input Fields: The Following should be Available but not limited to: 3.1 Textbox - For instances requiring text based input. 3.2 Button - Submit Button to confirm user input. 3.3 Email - For input that requires user Email. | Back-end Developers | 72 hrs
| HI-007 | Should be located on top of the Screen. | 1. Design a Webpage 2. Add a Navigation Bar 3. Create a Homepage 4. Create a Chat Page 5. Create an About Us Page 6. Create a Contact Us Page 7. Connect the following Pages to Navigation Bar 8. Connect Chatbot to Home Page using API 9. Conduct Test Run | Input Fields: The Following should be Available but not limited to: 6.1 Textbox - For instances requiring text based input. 6.2 Button - Submit Button to confirm user input. 6.3 Email - For input that requires user Email. | Project Manager UI/UX Designers Front-end Developers | 120 hrs
Sprint 3 Timeline: May 8 - May 19
Sprint Goal: Expansion and refinement of Website & addition of Emergency Contact Information | User Story Number | User Story | Tasks | Acceptance Criteria/Tasks | Assignee/s | Remarks (User Story Point)
| HI-005 | Should redirect User to a Physician/Emergency Hotline. | 1. Add Hyperlinks/Contact Information of Health Professionals/Medical Hotlines | Input Fields: The Following should be Available but not limited to: 4.1 Button - Submit Button to confirm user input. | Back-end Developers | 24 hrs
| HI-012 | Should contain Fill-up Form and be able to send Email to Business Email. | 1. Create a Fill up form for Contact Us 2. Generate PHP code to capture data 3. Conduct Test Run | Input Fields: The Following should be Available but not limited to: 11.1 Textbox - For instances requiring text based input. 11.2 Button - Submit Button to confirm user input. 11.3 Email - For input that requires user Email. | Project Manager UI/UX Designers Front-end Developers | 72 hrs
| HI-014 | Should have a welcome splash screen. | 1. Create Page Outline 2. Fill in CSS and Title Information in <Head> Section 3. Add script to move onto Home Page 4. Add Logo 5. Add Button 6. Conduct Test Run | Animation: 13.1 Logo - Contains the Chatbot Logo. 13.2 Button - Submit Button to confirm user input. | Project Manager UI/UX Designers Front-end Developers | 24 hrs
Sprint 4: May 22 - May 26
Sprint Goal: (Reserved) | User Story Number | User Story | Tasks | Acceptance Criteria/Tasks | Assignee/s | Remarks (User Story Point)
| HI-012 | Should contain Fill-up Form and be able to send Email to Business Email. | 1. Create a Fill up form for Contact Us 2. Generate PHP code to capture data 3. Conduct Test Run | Input Fields: The Following should be Available but not limited to: 11.1 Textbox - For instances requiring text based input. 11.2 Button - Submit Button to confirm user input. 11.3 Email - For input that requires user Email. | Project Manager UI/UX Designers Front-end Developers | 72 hrs
| HI-014 | Should have a welcome splash screen. | 1. Create Page Outline 2. Fill in CSS and Title Information in <Head> Section 3. Add script to move onto Home Page 4. Add Logo 5. Add Button 6. Conduct Test Run | Animation: 13.1 Logo - Contains the Chatbot Logo. 13.2 Button - Submit Button to confirm user input. | Project Manager UI/UX Designers Front-end Developers | 24 hrs
Sprint 5 Timeline: June 5 - June 16
Sprint Goal: Implementation of Email Reminder Automation & Utilization of System Logging | User Story Number | User Story | Tasks | Acceptance Criteria/Tasks | Assignee/s | Remarks (User Story Point)
| HI-011 | Should utilize Google Sheets for user data and send Email Reminder on dsignated Date. | 1. Write Python Script 2. Connect to Google Sheets 3. Connect to SMTP Server 4. Create Email Template 5. Conduct Test Run | Automation: 10.1 Script - Contains the Python Program for Email Automation. | Back-end Developers | 120 hrs
| HI-009 | Should utilize Typebot's Built-in System. | 1. Organize and Set-up Typebot's Logging System | Data Handling: 8.1 Data Table - All Data stored in Tabular form. | Back-end Developers | 72 hrs
| HI-015 | Should record the number of times user clicks on a certain feature and reflect on the Database. | 1. Add Update Table function at the beginning of each Feature 2. Modify the Database in Google Sheets to accomodate Analytics 3. Conduct Test Run | Data Handing: 14.1 Data Table - All Data stored in Tabular form. 14.2 Column - Follow Naming Standards. | Back-end Developers | 72 hrs
| HI-014 | Should have a welcome splash screen. | 1. Create Page Outline 2. Fill in CSS and Title Information in <Head> Section 3. Add script to move onto Home Page 4. Add Logo 5. Add Button 6. Conduct Test Run | Animation: 13.1 Logo - Contains the Chatbot Logo. 13.2 Button - Submit Button to confirm user input. | Project Manager UI/UX Designers Front-end Developers | 24 hrs
Sprint 6 Timeline: June 19 - June 30
Sprint Goal: Extension of Sprint 5 & revisions on System Design | User Story Number | User Story | Tasks | Acceptance Criteria/Tasks | Assignee/s | Remarks (User Story Point)
| HI-011 | Should utilize Google Sheets for user data and send Email Reminder on dsignated Date. | 1. Write Python Script 2. Connect to Google Sheets 3. Connect to SMTP Server 4. Create Email Template 5. Conduct Test Run | Automation: 10.1 Script - Contains the Python Program for Email Automation. | Back-end Developers | 120 hrs
| HI-015 | Should record the number of times user clicks on a certain feature and reflect on the Database. | 1. Add Update Table function at the beginning of each Feature 2. Modify the Database in Google Sheets to accomodate Analytics 3. Conduct Test Run | Data Handing: 14.1 Data Table - All Data stored in Tabular form. 14.2 Column - Follow Naming Standards. | Back-end Developers | 72 hrs
| HI-016 | Should have a log-in system for Admins to view Analytics. Users will remain anonynmous, not requiring log-in. | 1. Look for an Appropriate Database for Log-in. 2. Create a log-in page. 3. Build a baseline log-in system. 4. Make use of Two Factor Authentication for log-in (Optional). 5. Conduct Test Run. | Input Fields: The Following should be Available but not limited to: 15.1 Textbox - For instances requiring text based input. 15.2 Button - Submit Button to confirm user input. 15.3 Email - For input that requires user Email. | Back-end Developers | 120 hrs
| HI-017 | Should have a Dashboard UI for Admins that shows a summary of the Analytics. | 1. Create an Analytics Page. 2. Divide the page into Graphics and Summary. 3. Integrate Database into Analytics Page. 4. Conduct Test Run. | Visualization: 16.1 Graphics - For instances requiring visualization of data. 16.2 Summary - For quick rundown view of analytics. | Front-end/Back-end Developers | 72 hrs
| HI-018 | Should utilize NLP/OpenAI Integration to avoid monotonous conversations. | 1. Integrate OpenAI for NLP. 2. Rework Conversation flow. 3. Remove Dialogue Management Algorithm 4. Conduct Test Run. | Chatbot Response: 17.1 Varied Responses - The responses of the Chatbot should not be scripted. | Back-end Developers | 120 hrs
Sprint 7 Timeline: July 3 - July 7
Sprint Goal: System Verification by a Professional, Creation of Feedback Page Survey & Continutation of Sprint 6 | User Story Number | User Story | Tasks | Acceptance Criteria/Tasks | Assignee/s | Remarks (User Story Point)
| HI-001 | Should be verified by a Physician. | 1. Survey Approval/Verification 2. Finish the Basic Chatbot System 3. Conduct Survey on a Physician | Conversation Content: 0.1 Chatbot Features | Team Lead/Assistants Researchers | 120 hrs
| HI-013 | Should contain a Survey regarding the Chatbot via Google Forms. | 1. Survey Approval/Verification 2. Create a Google Form 3. Create Feedback Page 4. Connect Google Form via Hyperlink | Input Fields: The Following should be Available but not limited to: 12.1 Textbox - For instances requiring text based input. 12.2 Button - Submit Button to confirm user input. 12.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 12.4 Date - For input that requires Custom Date. | Project Manager UI/UX Designers Front-end Developers Researchers | 72 hrs
| HI-015 | Should record the number of times user clicks on a certain feature and reflect on the Database. | 1. Add Update Table function at the beginning of each Feature 2. Modify the Database in Google Sheets to accomodate Analytics 3. Conduct Test Run | Data Handing: 14.1 Data Table - All Data stored in Tabular form. 14.2 Column - Follow Naming Standards. | Back-end Developers | 72 hrs
| HI-017 | Should have a Dashboard UI for Admins that shows a summary of the Analytics. | 1. Create an Analytics Page. 2. Divide the page into Graphics and Summary. 3. Integrate Database into Analytics Page. 4. Conduct Test Run. | Visualization: 16.1 Graphics - For instances requiring visualization of data. 16.2 Summary - For quick rundown view of analytics. | Front-end/Back-end Developers | 72 hrs

## Standards
User Interface Standards
Consistency | Navigation | Typography | Color | Feedback | Accessibility | Flexibility | User Testing
Chat field 1.1. The chat messages can be found at the center of the page 1.2. The chat input box will be placed below the chat messages 1.3. The send button will also be placed below the chat messages, beside the chat input field | Navigation Bar 1.1. Navigation bar can be found at the top of the page 1.2. Navigation bar wil have the following: - Chatbot Logo - Contact Us Button - Feedback Button - About Us button | Typography 1.1. Font - Open Sans 1.2 Font Size - 15 | The chatbot will add a selection of background wallpapers that have calming colors and design: 1. The wallpapers that will be used will be relaxing and can represent the user's emotion 1.1. A button will be applied so that the user can switch background wallpaper | The user enters a message: 1.1 The message will be sent if Send Button is pressed. 1.2 If the message is sent the chatbot will respond based on the answer as a Feedback. 1.3 If your message failed to send, a popup message will appear with instructions to reload the page. | The Send button will have the key "Enter" as a shortcut key | Users will be able to change the background wallpaper of the chatbot to suit their own preferences | The chatbot will be avilable for testing: 1.1. Respondents will test the chatbot to make sure the user experience is proper and intuitive. 1.2. The users can use the feedback button to share their insights on the current state of the system.
Coding Standards
Naming Conventions | Indentation | Comments | Code Structure | Error handling | Security | Performance | Version Control
Use descriptive and meaningful names for variables, functions, classes, and files. | Use 4 spaces for indentation. | Use comments to explain the purpose of the code. | Organize code into logical blocks and functions. | Use appropriate error handling techniques to catch and handle errors gracefully. | Use encryption, sanitization, and validation techniques to prevent attacks such as SQL injection or cross-site scripting. | Optimize code for performance by avoiding unnecessary loops and using efficient algorithms. | Use Git for version control
Use camelCase for naming variables and functions, and PascalCase for naming classes | Do not use tabs for indentation. | Use single-line comments for short explanations |  |  |  |  | Use branches for different features and bug fixes.
Use lowercase letters for file names. | Maintain consistent indentation throughout the code | Use multi-line comments for detailed explanations. |  |  |  |  | Use pull requests for code review and collaboration.
Comment out unused code instead of deleting it
Secure Coding Standards
Input Validation | Authentication and Authorization | Session Management | Error Handling | Cryptography | Input/Output Validation | Secure Coding Practices | Testing
Make sure that the input complies with the desired format and ranges by developing validation methods for each input field. |  | In order to lessen the danger of unwanted access, we will use a shorter session timeouts and will ask the user to reload. | Provide users general alerts for issues instead of general error messages to prevent displaying error messages that would otherwise expose sensitive information about the system. | Usage of strong cryptographic methods and sources of entropy like random number generators to produce encryption keys. | Codebase will be searched using automated methods like static and dynamic analysis tools for potential flaws like buffer overflows and injection attacks. | The chatbot will adhere to secure coding standards and practices, such as utilizing the most recent frameworks and libraries, avoiding hard-coding credentials and other sensitive information, and employing safe coding rules. | For the purpose of finding SayAI's vulnerabilities, penetration testing will be conducted. This entails simulating attacks on the system to find areas where it could be vulnerable to attack.
Ensure that all input data is clean to avoid injection attacks. |  | We will utilize secure session management strategies, such as the use of secure cookies, to avoid session hijacking and other threats. | Removing the inclusion of sensitive information in error messages or logs, such as server information or version numbers, or any other system information. Attackers may find flaws and take advantage of possible exploits to the system. | Sensitive data will be protected by the chatbot using industry-standard encryption techniques like RSA and AES, and key compromise will be avoided via secure key management procedures. | Utilization of a web application firewall (WAF) to monitor and filter incoming traffic for known threats, such as buffer overflows and injection attempts. | SayAI's software components, such as the operating system, web server, programming languages, and any third-party libraries or frameworks, will all undergo regular updates check. | To find any security flaws that might only be present in specific circumstances, SayAI will undergo testing in a variety of settings, including test and staging environments.

## System Requirements
System Name | Group Members | Statement of the Problem | Methodology to address SOP | System Modules | Submodules | User Stories (Requirements) | Acceptance Criteria
Group I – HIRAYA | Bellen, Mark Paul Luiz G. | What is the degree of the ability to cope with Stress of the Respondents? | Survey Questionnaire | Chatbot System | Conversation Flow/Content | Should be verified by a Physician. | Conversation Content: 0.1 Chatbot Features
| Lopez, Loyd Marion B. | How can Artificial Intelligence/Chatbots address Stress-related Issues of University Students? | Synthesis of RRL + Survey Questionnaire (“Effectiveness of Chatbot Features”) |  | Chat Simulation | Should be anthropomorphic whilst not utilizing Machine Learning/Advanced Artificial Intellligence. | Typing Emulation: The Following are characteristics that Emulate Human Chatting Behaviors: 1.1 Words per Minute [300] 1.2 Chat Response Delay [2.5 sec Max] 1.3 Chat Bubble
| Abenion, Jess Amiel | What is the perception of University Students towards the use of Chatbots? | Survey Questionnaire
|  | What is the degree of satisfaction of University Students after using the Chatbot Assistant? | Survey Questionnaire | Chatbot Features | Homework Help | Should be user-friendly/easy to use. | Input Fields: The Following should be Available but not limited to: 2.1 Textbox - For instances requiring text based input. 2.2 Button - Submit Button to confirm user input. 2.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 2.4 Date - For input that requires Custom Date.
Motivational Advice
[5 empty] | Event Reminder | Should be connected to Google Sheets and collect data via conversation. | Input Fields: The Following should be Available but not limited to: 3.1 Textbox - For instances requiring text based input. 3.2 Button - Submit Button to confirm user input. 3.3 Email - For input that requires user Email.
[5 empty] | Seek Professional Help | Should redirect User to a Physician/Emergency Hotline. | Input Fields: The Following should be Available but not limited to: 4.1 Button - Submit Button to confirm user input.
[5 empty] | Venting Mode | Should not collect any kind of Sensitive/Personal Data. | Data Handling: 5.1 Cached Data - All sensitive user input are Cached Data.
|  |  |  | Navigation Bar | Logo | Should be located on top of the Screen. | Input Fields: The Following should be Available but not limited to: 6.1 Button - Submit Button to confirm user input.
Home
Chat
About Us
[5 empty] | Contact Us | Should contain Fill-up Form and be able to send Email to Business Email. | Input Fields: The Following should be Available but not limited to: 11.1 Textbox - For instances requiring text based input. 11.2 Button - Submit Button to confirm user input. 11.3 Email - For input that requires user Email.
[5 empty] | Feedback | Should contain a Survey regarding the Chatbot via Google Forms. | Input Fields: The Following should be Available but not limited to: 12.1 Textbox - For instances requiring text based input. 12.2 Button - Submit Button to confirm user input. 12.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 12.4 Date - For input that requires Custom Date.
|  |  |  | Chat Page | Chatbot | Should utilize Dialogue Management System/Pre-defined Conversation. | Interface: 7.1 Chat Simulation UI
|  |  |  | Data Management | User ID | Should utilize Typebot's Built-in System. | Data Handling: 8.1 Data Table - All Data stored in Tabular form.
Bot ID
System Logs
[5 empty] | Name | Should be contained within Google Sheets. | Data Handling: 9.1 Data Table - All Data stored in Tabular form. 9.2 Column - Follow Naming Standards.
Email
Event Name
Date
|  |  |  | Automation | Automated Emailing System | Should utilize Google Sheets for user data and send Email Reminder on dsignated Date. | Automation: 10.1 Script - Contains the Python Program for Email Automation.
|  |  |  | Animation | Splash Screen | Should have a welcome splash screen. | Animation: 13.1 Logo - Contains the Chatbot Logo. 13.2 Button - Submit Button to confirm user input.
|  |  |  | Analytics | Activity Tracker | Should record the number of times user clicks on a certain feature and reflect on the Database. | Data Handing: 14.1 Data Table - All Data stored in Tabular form. 14.2 Column - Follow Naming Standards.
|  |  |  | Log-in Screen | Admin Account | Should have a log-in system for Admins to view Analytics. Users will remain anonynmous, not requiring log-in. | Input Fields: The Following should be Available but not limited to: 15.1 Textbox - For instances requiring text based input. 15.2 Button - Submit Button to confirm user input. 15.3 Email - For input that requires user Email.
|  |  |  | Dashboard | Analytics UI | Should have a Dashboard UI for Admins that shows a summary of the Analytics. | Visualization: 16.1 Graphics - For instances requiring visualization of data. 16.2 Summary - For quick rundown view of analytics.
|  |  |  | Artificial Intelligence | Chatbot Algorithm | Should utilize NLP/OpenAI Integration to avoid monotonous conversations. | Chatbot Response: 17.1 Varied Responses - The responses of the Chatbot should not be scripted.

## RTM
HIRAYA - Requirements Traceability Matrix
| BR/Ref No. | User Story/Business Requirement | Acceptance Criteria | For Dev Team to fill-up |  | For QA Team to fill-up
REF. NO. LEGEND |  |  |  | Ref. No | Solution Design/Module | Test Case No. | Test Case Title | Passed/Failed
M = Module 000 = Number A-Z = Submodule | HI-001 | Should be verified by a Physician. | Conversation Content: 0.1 Chatbot Features | M-001A | Chatbot System |  |  | Failed
TC = Test Case 000 = Number A-Z = Sprint No. | HI-002 | Should be anthropomorphic whilst not utilizing Machine Learning/Advanced Artificial Intelligence. | Typing Emulation: The Following are characteristics that Emulate Human Chatting Behaviors: 1.1 Words per Minute [300] 1.2 Chat Response Delay [2.5 sec Max] 1.3 Chat Bubble | M-001B | Chatbot System | TC-001A | Natural Conversation Test | Passed
| HI-003 | Should be user-friendly/easy to use. | Input Fields: The Following should be Available but not limited to: 2.1 Textbox - For instances requiring text based input. 2.2 Button - Submit Button to confirm user input. 2.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 2.4 Date - For input that requires Custom Date. | M-002A | Chatbot Features | TC-002A | Chatbot Feature Test | Passed
| HI-004 | Should be connected to Google Sheets and collect data via conversation. | Input Fields: The Following should be Available but not limited to: 3.1 Textbox - For instances requiring text based input. 3.2 Button - Submit Button to confirm user input. 3.3 Email - For input that requires user Email. | M-002B | Chatbot Features | TC-006B | Google Sheet Integration Test | Passed
| HI-005 | Should redirect User to a Physician/Emergency Hotline. | Input Fields: The Following should be Available but not limited to: 4.1 Button - Submit Button to confirm user input. | M-002C | Chatbot Features | TC-008C | Professional Help Feature | Passed
| HI-006 | Should not collect any kind of Sensitive/Personal Data. | Data Handling: 5.1 Cached Data - All sensitive user input are Cached Data | M-002D | Chatbot Features | TC-004B | Venting Mode Test | Passed
| HI-007 | Should be located on top of the Screen. | Input Fields: The Following should be Available but not limited to: 6.1 Button - Submit Button to confirm user input. | M-003A | Navigation Bar | TC-007B | Webpage Navigation Test | Passed
| HI-008 | Should utilize Dialogue Management System/Pre-defined Conversation. | Interface: 7.1 Chat Simulation UI | M-004A | Chat Page | TC-003A | Chatbot Algorithm Test | Passed
| HI-009 | Should utilize Typebot's Built-in System. | Data Handling: 8.1 Data Table - All Data stored in Tabular form. | M-005A | Data Management | TC-010E | Typebot Logging Test | Passed
| HI-010 | Should utilize Google Sheets | Data Handling: 9.1 Data Table - All Data stored in Tabular form. 9.2 Column - Follow Naming Standards | M-005B | Data Management | TC-005B | Data Storage Format | Passed
| HI-011 | Should utilize Google Sheets for user data and send Email Reminder on designated Date. | Automation: 10.1 Script - Contains the Python Program for Email Automation. | M-006A | Automation |  |  | Failed
| HI-012 | Should contain Fill-up Form and be able to send Email to Business Email. | Input Fields: The Following should be Available but not limited to: 11.1 Textbox - For instances requiring text based input. 11.2 Button - Submit Button to confirm user input. 11.3 Email - For input that requires user Email. | M-003B | Navigation Bar | TC-009D | Contact Us Function | Passed
| HI-013 | Should contain a Survey regarding the Chatbot via Google Forms. | Input Fields: The Following should be Available but not limited to: 12.1 Textbox - For instances requiring text based input. 12.2 Button - Submit Button to confirm user input. 12.3 Radio Buttons - For user selection of predetermined choices in Chatbot Flow. 12.4 Date - For input that requires Custom Date. | M-003C | Navigation Bar | TC-014G | Survey Test | Failed
| HI-014 | Should have a welcome splash screen. | Animation: 13.1 Logo - Contains the Chatbot Logo. 13.2 Button - Submit Button to confirm user input. | M-007A | Animation | TC-011E | Splash Screen Test | Passed
| HI-015 | Should record the number of times user clicks on a certain feature and reflect on the Database. | Data Handing: 14.1 Data Table - All Data stored in Tabular form. 14.2 Column - Follow Naming Standards. | M-008A | Analytics | TC-015G | Analytics Test | Passed
| HI-016 | Should have a log-in system for Admins to view Analytics. Users will remain anonynmous, not requiring log-in. | Input Fields: The Following should be Available but not limited to: 15.1 Textbox - For instances requiring text based input. 15.2 Button - Submit Button to confirm user input. 15.3 Email - For input that requires user Email. | M-009A | Log-in | TC-012F | Log-in System Test | Passed
| HI-017 | Should have a Dashboard UI for Admins that shows a summary of the Analytics. | Visualization: 16.1 Graphics - For instances requiring visualization of data. 16.2 Summary - For quick rundown view of analytics. | M-010A | Dashboard | TC-016G | Analytics Dashboard Test | Passed
| HI-018 | Should utilize NLP/OpenAI Integration to avoid monotonous conversations. | Chatbot Response: 17.1 Varied Responses - The responses of the Chatbot should not be scripted. | M-011A | Chatbot Algorithm | TC-013F | Word Recognition Test | Passed